## Gaant
| Task | Start date | End date | Duration | Parent task | Children tasks
Task 1 | Prepare project charter and get approval | 2024-02-08 | 2024-02-15 | 7 | Project start | Define project objectives Identify key stakeholders Draft project scope statement Review and finalize project charter
Task 2 | Define detailed requirements and get approval | 2024-02-15 | 2024-02-17 | 3 | Project start | Conduct stakeholder interviews Document functional requirements Document non-functional requirements Review and obtain approval for requirements document
Task 3 | Prepare project plan and get approval | 2024-02-18 | 2024-02-20 | 3 | Project start | Develop project schedule Develop resource plan Develop risk management plan Obtain approval for project plan
Task 4 | Project kickoff meeting | 2024-02-21 | 2024-02-21 | 1 | Project start | Plan agenda and invite stakeholders Conduct kickoff meeting Distribute meeting minutes and action items
Task 5 | Procure materials (software, hardware) | 2024-02-22 | 2024-02-28 | 7 | Project start | Identify required software and hardware Obtain quotes from vendors Negotiate contracts and purchase orders Receive and inspect materials
Task 6 | Install software and hardware | 2024-03-08 | 2024-03-14 | 7 | Project start | Set up servers and networking equipment Install and configure software applications Test hardware and software integration
Task 7 | Test system | 2024-03-15 | 2024-03-22 | 7 | Project start | Develop test cases and scenarios Execute system testing Document and report defects Retest resolved defects
Task 8 | Schedule training | 2024-03-23 | 2024-03-24 | 7 | Project start | Identify training needs Develop training materials Schedule training sessions Coordinate trainers and facilities
Task 9 | Train superusers | 2024-03-25 | 2024-03-27 | 2 | Schedule training | Conduct training sessions for superusers Provide hands-on practice and support Assess superusers' proficiency and readiness
Task 10 | Train end users | 2024-04-04 | 2024-04-04 | 3 | Schedule training | Conduct training sessions for end-users Provide user manuals and guides Address questions and concerns
Task 11 | Go live | 2024-04-04 | 2024-04-04 | 1 | Project start | Deploy system to production environment Monitor system performance Address any issues or disruptions
Task 12 | Post live support | 2024-04-05 | 2024-04-01 | 7 | Go live | Provide ongoing technical support Address user inquiries and issues Monitor system stability and performance